## Sheet1
Group | Task name | Min. hours | Max. hours | Rough average | Min. hours (Dev) | Max. hours (Dev) | Rough average(Dev) | Rough average(Dev)
LinkedIn Scraper | Total BE | 6.75 | 13.25 | 10
| Check if its possible to scrape linkedin in no xwindow linux and try to find a way if not possible | 0.5 | 1 | 0.75 | 0.75 | 1.5 | 1.25 | 1
| Python + selenium install & integration module | 0.5 | 1 | 0.75 | 0.75 | 1.5 | 1.25 | 1
| Parse profile page for all information related to given user (no coding) | 1 | 2 | 1.5 | 0.5 | 1.75 | 1.25 | 1.75
| Code for get all profile information | 1 | 1.5 | 1.25 | 0.75 | 1.25 | 1 | 1
| Export data in anyway (json, csv, mysql) | 0.75 | 1.25 | 1 | 0.5 | 1 | 0.75 | 0.75
| Make a module to keep session | 0.5 | 1.5 | 1 | 0.5 | 1.25 | 0.865 | 0.75
| Curl to send request to the scraping server and save response data to the database | 1 | 2 | 1.5 | 1 | 1.5 | 1.25 | 1
| Run the scraper, get result and respond to the main server | 0.5 | 1 | 0.75 | 0.25 | 0.75 | 0.5 | 0.5
| Test and Fixing | 1 | 2 | 1.5 | 0.75 | 1.5 | 1.25 | 1.25
blocket.se Scraper | Total | 16 | 28.5 | 22.25
| Check we can use scrapy instead of selenium | 2 | 3 | 2.5 | 1.75 | 2.5 | 2.125 | 2
| Check potential re-captcha | 1 | 1.5 | 1.25 | 0.75 | 1 | 0.865 | 1
| Check if API used and analyse of work flow | 1 | 2 | 1.5 | 0.75 | 1.5 | 1.125 | 1.25
| Gtranslate API integration | 1.5 | 2.5 | 2 | 1.25 | 2 | 1.125 | 1.75
| Transferwise or Google API integration | 2 | 4 | 3 | 1.75 | 3.5 | 2.625 | 2.75
| Car listing and Criteria to list certain products listing. ignore ads | 1.5 | 2 | 1.75 | 1.25 | 1.75 | 1.5 | 1.5
| Proxy rotation integration if needed | 1 | 2 | 1.5 | 1 | 1.75 | 1.375 | 1.5
| Parse product page for all items | 2 | 4 | 3 | 2 | 3.75 | 2.875 | 2.5
| DB setting and table construction | 1 | 2 | 1.5 | 0.75 | 1.75 | 1.25 | 1.25
| Code for all | 2 | 3.5 | 2.75 | 1.75 | 3.25 | 2.5 | 2.5
| Test and fixing | 1 | 2 | 1.5 | 0.75 | 1.75 | 1.25 | 1.25
| Install run time environment for running for a long time | 0.5 | 1 | 0.75 | 0.5 | 0.75 | 1.125 | 0.5